## Cross-Sell Playbook
Adoption Playbook Template |  | Key objectives of Adoption |  |  | Best Practices / Basic workflow
|  | To provide value through complementary products in an effort to increase NRR |  |  | Qualification of Accounts
Create a shortlist through a combination of factors such as account health, phase of the journey, utilization, product usage, NPS, geography, etc.
|  | For Executives |  |  | Discovery
|  | Access to Reports / Dashboard |  |  | Identify all information on the pain points and other desired outcomes that could be addressed through cross-sell. Also, what cross-sell means (licenses, add-on module, higher plan, etc.) for the customer.
|  | For Customer Success Leaders |  |  | Quantification and Presentation
|  | Ability to showcase CS as a revenue center - Increase NRR |  |  | Present the achievable outcomes / proposed value of cross-sell. If feasible, quantify pain points against ROI through cross-sell
|  | For Customer Success Managers |  |  | Proposal - Amended contract
|  | Incentives, Better performance, Enhance relationship |  |  | Close the cross-sell with formal agreement
Milestone | Week | Activity | Audience | Objective | Type | Description | SmartKarrot Tools
Planning | Week 1 | Create adoption deck | CSM |  | Task |  | Account Segment Customer List View Product Console Account Intelligence
| Week 1 | Share adoption deck and adoption strategy | CSM |  | Task |  | Key Contact / Champion Account / Success Plan Task / Success To-Do
| Week 1 | Work on sticky features based on business goals for training | CSM AE |  | Task |  | Account Notes
Implementation | Week 2 | Create business outcome based training plan | CSM |  | Task
| Week 2 | Share training schedule with all the stakeholders. | CSM / AE Customer Stakeholder/s |  | Touchpoint |  | Touchpoint (Add)
| Week 3 | Run tranining plan | CSM / AE Customer Stakeholder/s |  | Touchpoint |  | Touchpoint (Add)
| Week 3 | Consolidate traning response & feedback | CSM / AE Customer Stakeholder/s |  | Task |  | Touchpoint (Add)
| Week 3 | Share training discovery and feedback with stakeholder. | CSM / AE Customer Stakeholder/s |  | Touchpoint |  | Touchpoint (Add)
Tracking | Week 4-8 | Track usage metrics | CSM AE |  | Task |  | Define Cross-sell Expansion Account Notes
| Week 4-8 | Weekly connects to discuss progress | CSM |  | Touchpoint
| Week 8 | Present adoption tracking matrices with internal stakeholders. | CSM CSL AE |  | Task
| Week 8 | Share business outcomes achieved | CSM |  | Touchpoint