## Upsell Playbook
Upsell Playbook Template |  | Key objectives of Upsell |  |  | Best Practices / Basic workflow
|  | To address additional outcomes / provide more value in an effort to boost revenue |  |  | Qualification of Accounts
Create a shortlist through a combination of factors such as account health, phase of the journey, utilization, product usage, NPS, geography, etc.
|  | Through add-on features/functionalities/modules/licenses Attainment of other strategic goals Increase NRR |  |  | Discovery
Identify all information on the pain points and other desired outcomes that could be addressed through upsell. Also, what upsell means (licenses, add-on module, higher plan, etc.) for the customer.
|  | Showcase WIIFM for key personas |  |  | Quantification and Presentation
Present the achievable outcomes / proposed value of upsell. If feasible, quantify pain points against ROI through the upsell
|  | Executives, CSLs and CSMs |  |  | Proposal - Amended contract
Close the upsell with formal agreement
Milestone | Week | Activity | Audience | Objective | Type | Description | SmartKarrot Tools
Qualification | Week 1 | Analyze current list of identified accounts | CSM | Review the list of accounts identified through Upsell account segment | Task | Analyze the indicators to qualify each account Check on the health score, utilization, touchpoints, account notes Review product console for each account by persona | Account Segment Customer List View Product Console Account Intelligence
| Week 1 | Schedule Discovery | CSM | Schedule connect with stakeholders (1-1 or group) for feedback and to analyze additional pain points and/or other desired outcomes | Task | Identify relevant stakeholder by account Update account plan / success plan Schedule connect with customer | Key Contact / Champion Account / Success Plan Task / Success To-Do
| Week 1 | (Optional) Discuss internally with relevant stakeholders w.r.t. potential opportunity | CSM AE | Provide a heads-up to relevant stakeholders on poteential opportunities | Task | Discuss the accounts to ensure that the team are prepared at their end | Account Notes
Discovery | Week 2 | Prep | CSM | To consolidate all the available informatiton including identified pain points and other desired outcomes | Task | Create a use case deck addressing how the proposed upsell will add more value to the customer Identify gaps/questions that the customer needs to be asked
| Week 2 | Discovery Session | CSM / AE Customer Stakeholder/s | Connect with stakeholder/s (1-1 or group) for feedback and to validate pain points and/or other desired outcomes | Touchpoint | Validate understanding of the pain point and/or desired outcome Clarify questions to complete the use case deck | Touchpoint (Add)
| Week 2 | Customer Follow-up Email | CSM / AE Customer Stakeholder/s | Summary of discovery session | Touchpoint | Share a summary to ensure there are no misunderstanding on the outcome | Touchpoint (Add)
Quantification & Presentation | Week 3 | Review Discovery Call | CSM AE | To quantify the pain points/outcomes | Task | Quantify the pain points / outcomes through appropriate metrics Identify and record the value proposition (additional licenses, higher subscription plan, add-on modules) | Define Upsell Expansion Account Notes
| Week 3 | Schedule connect with customer | CSM | Schedule connect with stakeholders (1-1 or group) to review the value proposition | Task | Block time on customer calendar
| Week 3 | Review Final Deck | CSM CSL AE | Get inputs from the CSL | Task | Review deck and proposed value with CSL for any inputs
| Week 3 | Finalize Upsell Deck | CSM | Complete the Upsell deck including the proposed value | Task | Complete the deck including relevant metrics and inputs from CSL
| Week 3 | Upsell Proposal | CSM / AE Customer Stakeholder/s | Walk through of the proposed value & product demonstration (if needed) | Touchpoint | Present the proposed value to the customer addressing their pain point / outcomes and confirm their buy-in / alignment | Touchpoint (Add)
| Week 3 | Customer Follow-up Email | CSM / AE Customer Stakeholder/s | Summary of the Upsell value | Touchpoint | Share a summary including the upsell value and any next steps | Touchpoint (Add)
Proposal: Negotiation & Closure | Week 4 | Proposal | CSM / AE | Creation of a formal proposal | Task | Create a formal proposal for Upsell based on discussions
| Week 4 | Proposal Review | CSM CSL AE | Review the proposal with the CSL | Task | Review proposal with CSL for any inputs
| Week 4 | Send Proposal | CSM / AE Customer Stakeholder/s | Send out the proposal to the stakeholder/s | Touchpoint | Share the proposal to the stakeholder/s for review and feedback Follow-up with a call, if required | Touchpoint (Add)
| Week 4 | Sign Contract | CSM / AE Customer Stakeholder/s | Complete the process with an Upsell contract / addendum to original contract | Touchpoint | Share contract for signature to the customer Share the final signed contract to relevant teams internally for action (Tech team, finance team, CSL) | Touchpoint (Add) Account Notes